## Slide 1: Navigating the Permitting Process for Utility Projects in Stream Corridors
Presented by: Cory Trego
April 7, 2026

## Slide 2: Navigating the Permitting Process for Utility Projects in Stream Corridors
April 7th, 2026
Notes: Introduction
Name
Project Environmental Scientist
GFT for 3 years

## Slide 3
GFT Office Locations
Notes: Gannett Fleming and TranSystems merged in 2024 to create GFT
5,000 employees located in offices across the US and Canada
Expertise in transportation, water/wastewater, environmental, power, and architecture

## Slide 4: Presentation Outline
Regulatory Framework Overview
Determining the Right Permit Path
Permitting Timelines and Expectations
Mitigation Strategies
Key Takeaways and Best Practices

## Slide 5: Why does Permitting Matter?
Often a critical path for project delivery
Significantly influences schedule, cost, and design
Regulatory landscape changes over time
Key Takeaway: Early Permitting Planning = Fewer Delays and Lower Costs

## Slide 6: Common utility projects that may require permitting include….
Utility line stream crossings
New outfalls or intakes
Infrastructure protection
New pump stations

## Slide 7: Regulatory Framework Overview
Notes: Review the list of agencies with which water utilities may need to coordinate for projects

## Slide 8: Regulatory Framework Overview
Types of Permits
Water Obstruction and Encroachment Permits (Chapter 105)
  General Permits (GPs)
  Individual Permits (Joint Permit Application Process)
Floodplain Management/Restoration (Chapter 106)
Notes: There are many type of permits that may be required for a project from the state, county, or local municipalities, but the focus of this presentation will be on what are typically referred to as Chapter 105 permits, which deal with impacts to streams, wetlands, and floodplains
Also are permit for work within the floodplain that are considered restoration activities (removal of infrastructure and regrading to natural conditions), but these are less common for utility projects.

## Slide 9: Regulatory Framework Overview
What Triggers a Permit?
Work in streams, wetlands, floodplains, or floodways
  Temporary and permanent impacts
  Stream crossings
  Bank stabilization
  Site access impacts
Notes: If streams or wetlands will be impacted by a project, a permit will likely be required….we’ll talk about exceptions later on in the presentation.

## Slide 10: Determining the Right Permitting Path
Online Guidance documents: Permit Application Consulting Tool (PACT), ePermitting, publications
Notes: Utilize Dep’s online resources to evaluate which permit is required for your projects…these include PACT, technical guidance documents, and publications, such as the Guidelines for Maintaining Stream in your community

## Slide 11: Determining the Right Permitting Path
Resource Identification Tools
Notes: One of the earliest steps in the planning process is to identify what resources may be impacts by the project. Determine if there are streams and wetlands in the project area, if those resources have a specific designation (EV, HQ), if there are T&E species that may be present, and if there are historic resources that may be impacted. Many online resources are available to assist with the planning process.

## Slide 12: Determining the Right Permitting Path
Pre-application Process
  Recommended for any complex project
  Beneficial early in project development
  Requires information on wetland and stream/floodway impacts, preliminary project plans
  Use available planning tools (PNDI, PAShare, eMap, etc.)

## Slide 13: Determining the Right Permitting Path
T&E Species and Species of Concern Coordination
PNDI receipt required
Agency clearance or coordination
May involve surveys to determine presence/absence
Potential Timing Restrictions
Best case is to avoid impacts

## Slide 14: Determining the Right Permitting Path
Identify Resources or Conditions that may impact permit requirements
  Presence of wetlands, watershed size, T&E species, cultural or historic resources
Waiver of Permit Requirements
General Permits: faster, limited impacts
    Must meet pre-defined eligibility criteria
Individual Permits: More comprehensive, longer review
Notes: Waiver examples: Watersheds <100 acres, scientific data collection, maintenance of certain artificial ponds/reservoirs, restoration activities (environmental assessment required)
E&S not waived if over 5,000 sqft (CD approval) and NPDES for over 1 acre

## Slide 15: Determining the Right Permitting Path
Common General Permits:
  GP-3: Bank Stabilization, Bank Protection, and Gravel Bar Removal
  GP-4: Intake and Outfall Structures
  GP-5: Utility Line Stream Crossings
  GP-7: Minor Road Crossings
  GP-8: Temporary Road Crossings
  GP-11: Maintenance, Repair, Rehabilitation, or Replacement of an Existing Water Obstruction and Encroachment
Notes: Explain each permit type…

## Slide 16: Determining the Right Permitting Path
Individual Permits: Longer review periods, more complex impacts to water resources
  Projects that do not meet GP eligibility criteria
    Exceptional Value Streams/Wetlands
    T&E Species Present
    Significant stream impacts or channel modifications
    Significant wetland impacts
    Does not meet a pre-defined category

## Slide 17: Determining the Right Permitting Path
When possible, design projects to fit the requirements of General Permits
Early coordination is critical and can avoid costs delays and redesigns
Design for co-benefits with other programs (e.g. MS4)

## Slide 18: Permitting Timelines and Expectation
General Permits: Typically, 2-3 months review time
Individual Permits: Minimum of 3 months…plan for 6 months
Incompleteness Reviews and Technical Deficiencies add time
Notes: 30 day admin review; 60 day technical review plus 60 days to address each review letter

## Slide 19: Mitigation Strategies
Avoidance
Minimization
Compensation
    On-site restoration
    Mitigation Banks
    In-lieu fee program (seldom used)

## Slide 20: Mitigation Strategies
Monitoring Required for on-site mitigation (typically a minimum of 5 years)
  May require maintenance, repairs, and replanting
Purchase of credits from off-site mitigation banks can be expensive, but it eliminates permittee monitoring and maintenance responsibilities

## Slide 21: Takeaways and Best Practices
Start Coordination Early
Understand T&E requirements and limitations
Design to Avoid Impacts
  Alternative installation methods (e.g. HDD)
  Rerouting to avoid wetlands
  Plan ahead for access

## Slide 22: Takeaways and Best Practices
Avoid Common Delays
  Incomplete applications
  Incorrect impact calculations
  Insufficient alternative analyses
  Lack of design detail

## Slide 23: Thank You! – Questions?
CORY TREGO, PROJECT ENVIRONMENTAL SCIENTIST
1010 ADAMS AVENUE
AUDUBON, PA
P: 484.587.5268
E: CTREGO@GFTINC.COM